## Overall Metrics
/No Proyecto/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 26.4 | 24.7 | 26
Planned Time | 0.10139 |  | 0.45556
Actual Tiempo |  | 0.17361 | 0.49931
CPI (Cost-Performance Index) |  |  | 0.91
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 9.62 | 0 | 6.43
Total Defects/KLOC or equivalent | 57.7 | 38.8 | 51.4
Yield % | 83.3% | 75% | 81.2%
Code Review Rate | 770 | 3090 | 9330
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:01 AM el 8/03/2017